## Instructions
Instructions for completing this document
Header
Student | Name of the student
Date | Date when the project/assignment was started
Project | Name of the project/assignment
Language | Coding language
Content
Date | Date when the activity takes place. There may be multiple dates in one log, depending on the number of days used to complete the assignment. For the first entry, it must be the same as the one in the header.
Start | Time when the activity is started (HH:MM)
Stop | Time when the activity is stopped (HH:MM)
Break time | Amount of minutes spend in something else when performing the activity (e.g. time using whatsapp, facebook, email, etc.). If the break is more than 30 minutes, stop the activity and start a new entry in the log.
Actual time | Amount of minutes calculated using: (stop time - start time) - break time.
Phase | Phase within the software development life-cycle (e.g. analysis, design, implementation, testing). If the assignment involves research, study, use of tutorials, it can also be specified in this box.
Comments | Details regarding the work performed for the corresponding entry.
Total | Total amount of minutes used for the completion of the project/assignment.

## Time recording log
Student | Danie Elias Becerra |  |  |  | Date | 24/04/2018
Project | Individual Project |  |  |  | Language | JAVA
Date | Start | Stop | Break time(min) | Actual time(hrs:min) | Phase | Comments
2018-04-03 | 16:26 | 19:02 | 0:12 | 2:24 | Analysis | Project Proposal - Analyzed how to solve the problem. Found the 49 solutions for a 3D TicTacToe
17/04/2018 | 17:21 | 18:48 | 0:00 | 1:27 | Design | Created the class diagram
17/04/2018 | 16:14 | 21:42 | 0:40 | 4:48 | Implementation | Programming. Made the classes Menu and Player. Started the GUI´s and design of the GUI's of Players, Play_Frame. Started working on the class Game which is the logic.
19/04/2018 | 16:42 | 20:36 | 0:25 | 3:29 | Implementation | Continued working on the logic of the Game class, identififying the logic behind it and the possible ways of winning.
20/04/2018 | 9:22 | 11:36 | 0:30 | 1:44 | Implementation | Finished working on the logic and checking possible ways of winning.
20/04/2018 | 16:50 | 19:36 | 0:15 | 2:31 | Implementation | Worked on modifying the ObjectWriter and ObjectReader from code5 Partial 2 classes to receive a String filename and work with the TicTacToe. Included the File Chooser class.
22/04/2018 | 11:22 | 15:36 | 0:30 | 3:44 | Testing | Corrected some issues with the logic and receiving null variables in some classes. The cases of wining ran successfully.
24/04/2018 | 7:15 | 8:36 | 0:00 | 1:21 | Implementation | Added some final details on graphical aspects and disabled some buttons.
24/04/2018 | 8:36 | 8:40 | 0:00 | 0:04 | Testing | Made a final test of the game. It ran successfully.
[5 empty] | Total(hrs:min) | 21:28